## Slide 1: Project Planning

## Slide 2
The basic processes of project planning are:
Scope planning – specifying the in-scope requirements for the project to facilitate creating the work breakdown structure
Preparation of the work breakdown structure – spelling out the breakdown of the project into tasks and sub-tasks
Project schedule development – listing the entire schedule of the activities and detailing their sequence of implementation
Resource planning – indicating who will do what work, at which time, and if any special skills are needed to accomplish the project tasks
Budget planning – specifying the budgeted cost to be incurred at the completion of the project
Procurement planning – focusing on vendors outside your company and subcontracting
Risk management – planning for possible risks and considering optional contingency plans and mitigation strategies
Quality planning – assessing quality criteria to be used for the project
Communication planning – designing the communication strategy with all project stakeholders

## Slide 3
The planning phase refines the project’s objectives, which were gathered during the initiation phase. It includes planning the steps necessary to meet those objectives by further identifying the specific activities and resources required to com­plete the project. Now that these objectives have been recognized, they must be clearly articulated, detailing an in-depth scrutiny of each recognized objective. With such scrutiny, our understanding of the objective may change. Often the very act of trying to describe something precisely gives us a better understanding of what we are looking at. This articulation serves as the basis for the development of requirements. What this means is that after an objective has been clearly articulated, we can describe it in concrete (measurable) terms and identify what we have to do to achieve it.
Users will often begin describing their objectives in qualitative language. The project manager must work with the user to provide quantifiable definitions to those qualitative terms. These quantifiable criteria include schedule, cost, and quality measures. In the case of project objectives, these elements are used as measurements to determine project satisfaction and successful completion.
Subjective evaluations are replaced by actual numeric attributes.

## Slide 4
Example 1
A web user may ask for a fast system. The quantitative requirement should be all screens must load in under three seconds. Describing the time limit during which the screen must load is specific and tangible. For that reason, you’ll know that the requirement has been successfully completed when the objective has been met.
Example 2
Let’s say that your company is going to produce a holiday batch of eggnog. Your objective statement might be stated this way: Christmas Cheer, Inc. will produce two million cases of holiday eggnog, to be shipped to our distributors by October 30, at a total cost of $1.5 million or less. The objective criteria in this statement are clearly stated and successful fulfillment can easily be measured. Stakeholders will know that the objectives are met when the two million cases are produced and shipped by the due date within the budget stated.

## Slide 5: Project Planning Terms
Deliverable: The results of a project, such as a product, service, report, etc.
Stakeholder: Anyone with a vested interest in the project—project manager, project sponsor, team members, customers, etc.
Tasks: Small jobs that lead to the final deliverable.
Milestone: The end of one project phase, and the beginning of the next.
Resources: Anything you need to complete the project, such as personnel, supplies, materials, tools, people and more.
Budget: Estimate of total cost related to completing a project.
Tracking & Monitoring: Collecting project data, and making sure it reflects the results you planned for.

## Slide 6: Project Planning Steps
1. Outline the business/academic case
2. Meet with key stakeholders
3. Define project scope
4. Assemble a project team
5. Determine a project budget
6. Set project goals & objectives
7. Outline project deliverables
8. Create a project schedule
9. Assign tasks to your team members
10. Do a risk analysis
11. Create your project plan
12. Report your progress

## Slide 7
Outline the Business Case
If you have a project, there’s a reason for it—that’s your business case.
The business case outlines reasons why the project is being initiated, its benefits and the return on investment. If there’s a problem that is being solved, then that problem is outlined here.
The business case will be presented to those who make decisions at your organization, explaining what has to be done, and how, along with a feasibility study to assess the practicality of the project.
If approved, you have a project

## Slide 8
2. Meet with Key Stakeholders
Every project has stakeholders, those who have a vested interest in the project. From the ones who profit from it, to the project team members who are responsible for its success. Therefore, any project manager must identify who these key stakeholders are during the project planning process, from customers to regulators. Meeting with them is crucial to get a better picture of what the project management plan should include and what is expected from the final deliverable.
3. Define Project Scope
It refers to the work required to accomplish the project objectives and generate the required deliverables. The project scope should be defined and organized by a work breakdown structure (WBS). Therefore, the project scope includes what you must do in the project (deliverables, sub deliverables, work packages, activities, tasks), but also what is nonessential. The latter is important for the project plan, because knowing what isn’t high priority helps to avoid scope creep; that is, using valuable resources for something that isn’t key to your project’s success.
4. Assemble a Project Team
You’ll need a capable project team to help you create your project plan and execute it successfully. It’s advisable to gather a diverse group of experienced professionals to build a multi-disciplinary team that sees your project management plan from different perspectives.

## Slide 9
5. Determine a Project Budget
Once you define your project scope, you’ll have a task list that must be completed to deliver your project successfully. To do so, you’ll need resources such as equipment, materials, human capital, and of course, money. Your project budget will pay for all this. The first step to create a project budget is to estimate the costs associated with each task. Once you have those estimated costs, you can establish a cost baseline, which is the base for your project budget.
6. Set Project Goals & Objectives
Goals and objectives are different things when it comes to planning a project. Goals are the results you want to achieve, and are usually broad. Objectives, on the other hand, are more specific; measurable actions that must be taken to reach your goal. When creating a project plan, the goals and objectives naturally spring from the business case, but in this stage, you go into further detail. In a sense, you’re fine-tuning the goals set forth in the business case and creating tasks that are clearly defined. These goals and objectives are collected in a project charter, which you’ll use throughout the project life cycle.
7. Outline Project Deliverables
A project can have numerous deliverables. A deliverable can be a good, service or result that is needed to complete a task, process, phase, subproject or project. For example, the final deliverable is the reason for the project, and once this deliverable is produced, the project is completed. As defined in the project scope, a project consists of subprojects, phases, work packages, activities and tasks, and each of these components can have a deliverable. The first thing to do is determine what the final deliverable is, and how you will know that the quality meets your stakeholder’s expectations. As for the other deliverables in the project, they must also be identified and someone on the team must be accountable for their successful completion.

## Slide 10
When articulating the project objectives you should follow the SMART rule:
Specific – get into the details. Objectives should be specific and written in clear, concise, and under­standable terms.
Measurable – use quantitative language. You need to know when you have successfully completed the task.
Acceptable – agreed with the stakeholders.
Realistic – in terms of achievement. Objectives that are impossible to accomplish are not realistic and not attainable. Objectives must be centered in reality.
Time based – deadlines not durations. Objectives should have a time frame with an end date assigned to them.

## Slide 11
8. Create a Project Schedule
The project schedule is what everything hangs on. From your tasks to your budget, it’s all defined by time. Schedules are made up by collecting all the tasks needed to reach your final deliverable, and setting them on a project timeline that ends at your deadline. This can make for an unruly job ahead, which is why schedules are broken into phases, indicated by milestones, which mark the end of one project phase and the beginning of the next.
9. Assign Tasks to Your Team Members
The plan is set, but it still exists in the abstract until you take the tasks on your schedule and begin assigning them out to your team members. Their roles and responsibilities must be clearly defined, so they know what to do. Then, when you assign them tasks from your plan, they should be clear, with directions and any related documentation they will need to execute the tasks.
10. Do a Risk Analysis
Every project has some level of risk. There are several types of risk such as scope risk, technical risks and schedule risk, among others. Even if your project plan is thorough, internal and external factors can impact your project’s time, cost and scope (triple constraint). Therefore, you need to regard your planning as flexible. There are many ways to prepare for risk, such as developing a change management plan, but for now, the most important thing to do is to track your progress throughout the execution phase by using project status reports and/or project planning software to monitor risk.

## Slide 12
11. Create your Project Plan
As discussed above, a project management plan is a document that’s made of several elements. Before we get into a detailed explanation of each of them, it’s important to understand that you should include them all to have a solid project plan. The components that you’ll need might vary depending on your project, but in general terms, you’ll need these main documents to create your project management plan:
Project charter
Project schedule
Project budget
Project scope statement
Risk management plan
Change management plan
Cost management plan
Resource management plan
Stakeholder management plan

## Slide 13
12. Report Your Progress
Your ultimate goal is to ensure a successful project for your stakeholders. They’re invested, and will not be satisfied twiddling their thumbs without looking at project status reports to track progress. By constructing a work breakdown structure (WBS) during the project planning phase you can break down the project for them so that they understand how your project plan will be executed. Keeping stakeholders informed is important to manage their expectations and ensure that they’re satisfied. Having regular meetings where you present progress reports are a great way to show them that everything is moving forward as planned and to field any questions or concerns they might have. Your stakeholder management plan will specify how you’ll engage stakeholders in the project.

## Slide 14
References
Project Plan. Retrieved on September 11, 2021 from https://www.projectmanager.com/project-planning
Overview of Project Planning. Retrieved on September 11, 2021 from https://opentextbc.ca/projectmanagement/chapter/chapter-8-overview-of-project-planning-project-management/